## Backlog
Construction of Hospital Building
Timeline of project : 8 Month
Month | Sprint | User Story | Task | Assignee | Story Points | Priority | Status | Timeline
Month 1 | Site Preparation & Foundation | As a project manager, I want to clear the site and prepare the foundation so that the hospital structure can be built. | Site clearing and excavation | Civil Engineering Team | 8 | High | Complete | Week 1-2
|  | As a project manager, I want to lay the foundation so that the hospital building can be constructed safely. | Pour concrete foundation | Construction Team | 13 | High | Complete | Week 2-4
|  | As a project manager, I want to conduct soil testing to ensure the land is stable for construction. | Soil stability tests | Environmental Engineer | 5 | Medium | Complete | Week 3-4
Month 2 | Structural Framework | As a project manager, I want the structural framework to be built so that the building can take shape. | Install steel framework | Steel Fabrication Team | 13 | High | Complete | Week 5-6
|  | As an architect, I want the framework to be aligned with the architectural plan. | Structural alignment check | Quality Assurance Team | 3 | Medium | Complete | Week 6
|  | As a project manager, I want to install the temporary scaffolding to support workers and materials. | Scaffold installation | Construction Team | 5 | Medium | Complete | Week 6-7
Month 3-4 | MEP (Mechanical, Electrical, Plumbing) Rough-In | As a hospital administrator, I want all utilities to be installed for a functional hospital. | Install plumbing pipes | Plumbing Team | 8 | High | Incomplete | Week 7-9
|  | As a hospital administrator, I want all electrical systems to be installed for hospital operations. | Wiring for electrical systems | Electrical Team | 13 | High | Complete | Week 7-9
|  | As a hospital administrator, I want HVAC systems to be in place to ensure proper climate control. | Install HVAC ducts | HVAC Team | 8 | High | Complete | Week 8-9
Month 4-5 | Exterior & Roofing | As a project manager, I want to complete the exterior walls and roofing for the building’s protection. | Install exterior walls | Construction Team | 13 | High | Complete | Week 10-11
|  | As a project manager, I want the roof to be waterproof to prevent any leaks. | Roofing installation | Roofing Team | 8 | High | Complete | Week 10-11
|  | As a project manager, I want all windows and doors installed. | Window and door installation | Construction Team | 8 | Medium | incomplete | Week 1
Month 5-6 | Interior Walls & Finishes | As a hospital administrator, I want the interior walls to be in place so we can begin partitioning spaces for different departments. | Install interior partitions | Interior Construction Team | 13 | High | Complete | Week 12-13
|  | As a hospital administrator, I want the walls to be painted for a clean and welcoming environment. | Interior painting | Painting Team | 8 | Medium | Complete | Week 13-14
|  | As a project manager, I want the floor finishes completed to meet safety and aesthetic standards. | Floor tiling and finishing | Flooring Team | 8 | Medium | Complete | Week 13-14
Month 6-7 | Final MEP & Testing | As a hospital administrator, I want all MEP systems to be operational so that the hospital is fully functional. | Test plumbing systems | Plumbing Team | 5 | High | Complete | Week 15-16
|  | As a hospital administrator, I want all electrical systems to be fully tested and functional. | Test electrical systems | Electrical Team | 8 | High | Complete | Week 15-16
|  | As a hospital administrator, I want to ensure HVAC systems are fully functional. | HVAC system testing | HVAC Team | 5 | High | Complete | Week 16
Month 7 | Furniture & Medical Equipment Setup | As a hospital administrator, I want the building furnished with hospital-grade furniture. | Install hospital furniture | Furniture Team | 8 | High | Complete | Week 17-18
|  | As a hospital administrator, I want medical equipment to be set up in designated areas. | Install medical equipment | Medical Equipment Team | 13 | High | Complete | Week 17-18
|  | As a project manager, I want the IT infrastructure to be installed. | Install IT systems | IT Team | 8 | Medium | Complete | Week 18
Month 8 | Final Inspection & Handover | As a hospital administrator, I want to ensure the hospital meets safety standards. | Safety inspection | Safety Inspector | 5 | High | Complete | Week 19-20
|  | As a hospital administrator, I want the final walk-through to confirm the building is ready for operations. | Final inspection and walk-through | Project Manager | 5 | High | Complete | Week 20
|  | As a hospital administrator, I want to hand over the building to the operations team. | Handover documentation and keys | Project Manager | 3 | High | Inprogress | Week 20

## Sprint 1
Sprint 1 (Month 1)
User Story | Task | Assignee | Story Point | Priority | Status | Timeline
As a project manager, I want to clear the site and prepare the foundation so that the hospital structure can be built. | Site clearing and excavation | Civil Engineering Team | 8 | High | Complete | Week 1-2
As a project manager, I want to lay the foundation so that the hospital building can be constructed safely. | Pour concrete foundation | Construction Team | 13 | High | Complete | Week 2-4
As a project manager, I want to conduct soil testing to ensure the land is stable for construction. | Soil stability tests | Environmental Engineer | 5 | Medium | Complete | Week 3-4

## Sprint 2
Sprint 2 (Month 2)
User Story | Task | Assignee | Story Point | Priority | Status | Timeline
As a project manager, I want the structural framework to be built so that the building can take shape. | Install steel framework | Steel Fabrication Team | 13 | High | Complete | Week 5-6
As an architect, I want the framework to be aligned with the architectural plan. | Structural alignment check | Quality Assurance Team | 3 | Medium | Complete | Week 6
As a project manager, I want to install the temporary scaffolding to support workers and materials. | Scaffold installation | Construction Team | 5 | Medium | Complete | Week 6-7

## Sprint 3
Sprint 3 (Month 3-4)
User Story | Task | Assignee | Story Point | Priority | Status | Timeline
As a hospital administrator, I want all utilities to be installed for a functional hospital. | Install plumbing pipes | Plumbing Team | 8 | High | Incomplete | Week 7-9
As a hospital administrator, I want all electrical systems to be installed for hospital operations. | Wiring for electrical systems | Electrical Team | 13 | High | Complete | Week 7-9
As a hospital administrator, I want HVAC systems to be in place to ensure proper climate control. | Install HVAC ducts | HVAC Team | 8 | High | Complete | Week 8-9

## Sprint 4
Sprint 4 (Month 4-5)
User Story | Task | Assignee | Story Point | Priority | Status | Timeline
As a project manager, I want to complete the exterior walls and roofing for the building’s protection. | Install exterior walls | Construction Team | 13 | High | Complete | Week 10-11
As a project manager, I want the roof to be waterproof to prevent any leaks. | Roofing installation | Roofing Team | 8 | High | Complete | Week 10-11
As a project manager, I want all windows and doors installed. | Window and door installation | Construction Team | 8 | Medium | incomplete | Week 11

## Sprint 5
Sprint 5 (Month 5-6)
User Story | Task | Assignee | Story Point | Priority | Status | Timeline
As a hospital administrator, I want the interior walls to be in place so we can begin partitioning spaces for different departments. | Install interior partitions | Interior Construction Team | 13 | High | Complete | Week 12-13
As a hospital administrator, I want the walls to be painted for a clean and welcoming environment. | Interior painting | Painting Team | 8 | Medium | Complete | Week 13-14
As a project manager, I want the floor finishes completed to meet safety and aesthetic standards. | Floor tiling and finishing | Flooring Team | 8 | Medium | Complete | Week 13-14

## Sprint 6
Sprint 6 (Month 6-7)
User Story | Task | Assignee | Story Point | Priority | Status | Timeline
As a hospital administrator, I want all MEP systems to be operational so that the hospital is fully functional. | Test plumbing systems | Plumbing Team | 5 | High | Complete | Week 15-16
As a hospital administrator, I want all electrical systems to be fully tested and functional. | Test electrical systems | Electrical Team | 8 | High | Complete | Week 15-16
As a hospital administrator, I want to ensure HVAC systems are fully functional. | HVAC system testing | HVAC Team | 5 | High | Complete | Week 16

## Sprint 7
Sprint 7 (Month 7)
User Story | Task | Assignee | Story Point | Priority | Status | Timeline
As a hospital administrator, I want the building furnished with hospital-grade furniture. | Install hospital furniture | Furniture Team | 8 | High | Complete | Week 17-18
As a hospital administrator, I want medical equipment to be set up in designated areas. | Install medical equipment | Medical Equipment Team | 13 | High | Complete | Week 17-18
As a project manager, I want the IT infrastructure to be installed. | Install IT systems | IT Team | 8 | Medium | Complete | Week 18

## Sprint 8
Sprint 7 (Month 7)
User Story | Task | Assignee | Story Point | Priority | Status | Timeline
As a hospital administrator, I want to ensure the hospital meets safety standards. | Safety inspection | Safety Inspector | 5 | High | Complete | Week 19-20
As a hospital administrator, I want the final walk-through to confirm the building is ready for operations. | Final inspection and walk-through | Project Manager | 5 | High | Complete | Week 20
As a hospital administrator, I want to hand over the building to the operations team. | Handover documentation and keys | Project Manager | 3 | High | Inprogress | Week 20

## BUDGET
BUDGET
| Total Budget | Receive Amount | Balance Payment | Saved Amount
| 22285000 | 10000000 | 12285000 | 50000
Expences
Assignee Team | Cost Of Team (contract amount) |  | Construction Material Cost |  | Miscellaneous
Civil Engineering Team | 2500000 |  | 9500000 |  | 500000
Construction Team | 1000000
Environmental Engineer | 900000
Steel Fabrication Team | 850000
Quality Assurance Team | 790000
Plumbing Team | 640000
Electrical Team | 620000
HVAC Team | 590000
Roofing Team | 580000
Interior Construction Team | 400000
Painting Team | 850000
Flooring Team | 790000
Furniture Team | 400000
Medical Equipment Team | 850000
IT Team | 25000
Safety Inspector | 50000
Project Manager | 900000
Amount | 12735000 |  | 9500000 |  | 50000
Total Amount Spend | 22285000